Goals and milestones:

Year 1:

- Triplet polarimeter (GlueX):

  - By October 2019, new backup amplification board for the triplet polarimeter will be built.

  - By November 2019, all of the 2018 data from the triplet polarimeter for the GlueX collaboration will be analyzed.

  - By January 2020, Graduate student Brandon Sumner will have obtained hands-on experience with the triplet polarimeter.

  - By September 2020 Sebastian and I will have upgraded the triplet polarimeter.

- Hybrid meson analysis (GlueX):

  - Currently, graduate student Sebastian Cole has signals for his initial K* K analysis (see: draft of presentation to be given tomorrow   https://userweb.jlab.org/~dugger/glueX/tmp/KStarKTmp1.pdf )

  - By January 2020, Sebastian is expected to have binned his K* K data in kinematic bins of |t| and Eγ, normalized the data using the incident photon flux and performed a Monte Carlo simulation for determination of the detector efficiency. He will have create cross sections in preparation of performing a PWA of the data.

  - By September 2020, Sebastian will have performed a PWA of his K* K cross section measurements.

- Cascade analysis (GlueX):

  - By January 2020 Brandon Sumner and the PI will have investigated all of the common cascade decay channels (Ξ* → Ξ π, Ξ* → Λ K, Ξ*→Σ K, Ξ* → Ξ(1530) π) and Brandon Sumner will have taken over the cascade analysis (see    https://userweb.jlab.org/~dugger/glueX/tmp/glueXAnaV2c.pdf for a recent talk from the PI).

  - By August 2020 Brandon will have created cross sections binned in cosϑcm and Eγ     for at least one Ξ* decay.

- Search for strangeness (CLAS12)

  - The PI will attend meeting of the Very Strange Group and assist in the determination of Λ, Σ and Ξ baryons. The determination of the Λ baryons will the highest priority and is crucial for the future success of the Very Strange Group.

Year 2:

- TPOL (GlueX):

  - By January 2021, Brandon Sumner will have written software for the determination of polarization that takes into account the new angular resolution capabilities of the TPOL device.

- Hybrid meson analysis (GlueX):

  - By the end of the Fall semester of 2020, Sebastian will have successfully defended his dissertation on the PWA of γ p → p K* K.

  - In January of 2021, a new graduate student will have entered the group to work on K* K data that includes DIRC data.

  - By January 2022, the new student will have helped others in the GlueX   collaboration with reconstruction and efficiency studies suitable for reliable use of DIRC data in GlueX analyses.

- Cascade analysis (GlueX):

  - By January 2021 Brandon will have cross section data for all of the Ξ* decay chains and started his PWA analysis.

- Search for strangeness (CLAS12)

  - The PI will continue to assist in analysis issues that arise regarding strangeness production using CLAS12 and will help coordinate the efforts of the Very Strange Group.

Year 3:

- Hybrid meson analysis (GlueX):

  - By September 2022 cross sections for all the DIRC data, available by this time, for K* K states will be produced and a PWA will have begun.

- Cascade analysis (GlueX):

  - By January 2022 Brandon will have finished his PWA analysis.

  - By May 2022 Brandon will have successfully defended his dissertation on the PWA of Ξ* states.

- Search for strangeness (CLAS12)

  - The PI will continue to assist in analysis issues that arise regarding strangeness production using CLAS12 and will help coordinate the efforts of the Very Strange Group.